## Running Orders
| Project Name | Project Deadline Date | Remaining Date | Sales Man | Total Ammount | Completed Ammount | Current Working | Status
ali_a01 | AI-powered healthcare website ¦¦ | 2024-12-29 | 0 | SHOVON | 2000 | 0 | Frontend | Inprogress
amd1923 | memory writer app | 2024-12-29 | 0 | Mim | 1600 | 400 | Frontend | Inprogress
albertolorente | Multilingual Audio App | 2024-12-23 | 0 | Toki | 4800 | 1200 | Backend + AI | Inprogress
kielspicer84 | Riptide Radar application | 2024-12-23 | 0 | Sanjida | 4800 | 1000 | AI | Inprogress
capinha08 | MEDworld App |  |  | Toki | 2000 | 0 | Deployment | Inprogress
shayne_philiber | Lone Star Ledger App | 2024-12-16 | 0 | ovi | 3200 | 0 | Frontend | Inprogress
Postyxbt | AutoGenAI | 2025-01-23 |  | Shazid | 800 | 0 | Backend + AI | Inprogress
adamos007 | AI Language Learning App | 2025-01-05 | 7 | Toki | 3600 | 0 | Figma | Inprogress
mikenieciecki | Health Care website | 2025-01-16 |  | Mahmud | 4200 | 0 | Figma | Inprogress
agcourt | website and application | 2025-01-17 | 0 | Rakhi | 650 | 0 | Figma | Inprogress
Alanbrb -- | AI-based virtual assistant platform |  |  | Anik | 2640 | 0 | Figma | Inprogress
Tyler B -- | Application |  |  | Anik | 2800 | 0 | Figma | Inprogress
fradituri | Ai Doctor App |  |  |  | 1920 | 0 | Figma | Inprogress
dianadiaz12 -- | Specksmart Application |  |  |  | 7280 | 0
Abdulai556 | AI-Restaurant operations |  |  |  | 4400 | 0
mrrc12 | Custom AI chatbot |  |  |  | 500 | 0
davisdebard | Ai website |  |  |  | 1760 | 0
dxteng | Custom WhatsApp Business Integration |  |  |  | 2080 | 0
aydtube | Smart watch Application |  |  |  | 5600 | 0
| AI-Powered Resume Optimization |  |  |  | 2000 | 0
nftking |  |  |  |  | 1400 | 0
egolden96 | Real estate services web&app |  |  |  | 4640 | 0
rnichaelzhu | Ai website |  |  |  | 560
adriancolonb | AI Website |  |  |  | 640
Fabiggz123 | Influencer website modification
Formulas:
Remaining Date = MAX(0, [Project Deadline Date]-TODAY())
Remaining Date = MAX(0, [Project Deadline Date, row above]-TODAY())

## Progress Report
Client Name
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0 | 0 | 0 | None
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
ali_a01
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-23 | 0 | 90% | Not delivered | None | 300 | 300 | 0 | -1400 | 2500 | Inprogress
Shakil | React.js |  | 0 | 0% | Not delivered | None | 700 | 0 | -700
Pial | Django |  | 0 | 0% | Not delivered | None | 700 | 0 | -700
Rafsun | AI |  | 0 | 0% | None | None | 300 | 0
None | Deployment |  | 0 | 0% | None | None | 0 | 0 | 0
amd1923
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Rafi | Flutter |  | 0 | 100% | Deliverd | Jan | 300 | 0 | -300
Shakil | React.js |  | 0 | 100% | Deliverd | Jan | 300 | 0 | -300
Shuvo | Node.js |  | 0 | 0% | None | None | 450 | 0
Fahad | AI |  | 0 | 0% | None | None | 300 | 0
None | Deployment |  | 0 | 0% | None | None | 0 | 0 | 0
albertolorente
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pial | Django |  | 0 | 0% | None | None | 1000 | 0 | -1000
Fahad | AI |  | 0 | 0% | None | None | 1400 | 0
None | Deployment |  | 0 | 0% | None | None | 500 | 0 | -500
capinha08
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 100% | Deliverd | Dec | 250 | 0 | -250 | -1950 | 0 | None
Ibrahim | Flutter | 2024-11-22 | 0 | 100% | Deliverd | Dec | 850 | 0 | -850
Ibrahim | Django | 2024-11-22 | 0 | 100% | Deliverd | Dec | 850 | 0 | -850
shayne_philiber
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 100% | Deliverd | Dec | 350 | 0 | -350
Mir | Flutter | 2024-11-23 | 0 | 100% | Deliverd | Jan | 650 | 0
Pial | Django | 2024-11-22 | 0 | 0% | None | None | 950 | 0 | -950
Fahad | AI | 2024-11-22 | 0 | 0% | None | None | 950 | 0
Postyxbt
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Mir | Flutter | 2024-11-22 | 0 | 0% | None | None | 500 | 0 | -500 | -800 | 0 | Inprogress
Bashar | AI | 2024-11-22 | 0 | 0% | None | None | 300 | 0 | -300
adamos007
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pappu | Figma | 2024-11-22 | 0 | 100% | Deliverd | Jan | 450 | 0 | -450 | -2500 | 0 | Inprogress
Mir | Flutter | 2024-11-22 | 0 | 0% | None | None | 1150 | 0 | -1150
Shuvo | Node.js | 2024-11-22 | 0 | 0% | None | None | 900 | 0 | -900
Fahad | AI | 2024-11-22 | 0 | 0% | None | None | 1100 | 0
mikenieciecki
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2025-01-16 | 0 | 0% | None | None | 560 | 0 | -560 | -3360 | 0 | Inprogress
Ibrahim | React.js | 2025-01-17 | 1 | 0% | None | None | 1400 | 0 | -1400
Ibrahim | Django | 2025-01-18 | 2 | 0% | None | None | 1400 | 0 | -1400
Alanbrb
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pappu | Figma | 2024-11-22 | 0 | 0% | None | None | 340 | 0 | -340 | -1840 | 0 | None
Shakil | React.js | 2024-11-22 | 0 | 0% | None | None | 800 | 0 | -800
Pial | Django | 2024-11-22 | 0 | 0% | None | None | 800 | 0
Fahad | AI | 2024-11-22 | 0 | 0% | None | None | 700 | 0 | -700
None | Deployment | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
Tyler B
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 100% | Deliverd | Jan | 450 | 0 | -450 | -2050 | 0 | None
Bijoy | React.js | 2024-11-22 | 0 | 100% | Deliverd | Jan | 850 | 0 | -850
Sadiqul | Django | 2024-11-22 | 0 | 0% | None | None | 750 | 0
Mahmood | AI | 2024-11-22 | 0 | 0% | None | None | 750 | 0 | -750
fradituri
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 100% | Deliverd | Jan | 250 | 0 | -250 | -1450 | 0 | None
Rafi | Flutter | 2024-11-22 | 0 | 100% | Deliverd | Jan | 600 | 0 | -600
Bijoy | React.js |  | 0 | 100% | Deliverd | Jan | 100
Shuvo | Node.js | 2024-11-22 | 0 | 0% | None | None | 600 | 0 | -600
Bashar | AI | 2024-11-22 | 0 | 0% | None | None | 400 | 0
None | Deployment | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
dianadiaz12
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 0% | None | None | 700 | 0 | -700 | -5500 | 0 | None
Mir | Flutter | 2024-11-22 | 0 | 0% | None | None | 1850 | 0 | -1850
Pial | Django | 2024-11-22 | 0 | 0% | None | None | 1850 | 0 | -1850
Bashar | AI | 2024-11-22 | 0 | 0% | None | None | 1779 | 0
Shakil | React.js | 2024-11-22 | 0 | 0% | None | None | 1100 | 0 | -1100
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
Abdulai556
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 0% | None | None | 500 | 0 | -500 | -3350 | 0 | None
Bijoy | React.js | 2024-11-22 | 0 | 0% | None | None | 700 | 0 | -700
Shuvo | Node.js | 2024-11-22 | 0 | 0% | None | None | 1050 | 0 | -1050
Mahmood | AI | 2024-11-22 | 0 | 0% | None | None | 1050 | 0
Mir | Flutter | 2024-11-22 | 0 | 0% | None | None | 1100 | 0 | -1100
mrrc12
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Ibrahim | React.js | 2024-11-22 | 0 | 100% | Deliverd | Jan | 200 | 0 | -200
Bashar | AI | 2024-11-22 | 0 | 100% | Deliverd | Jan | 200 | 0 | -200
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
davisdebard
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pappu | Figma | 2024-11-22 | 0 | 100% | Deliverd | Jan | 310 | 0 | -310 | -1160 | 0 | None
Bijoy | React.js | 2024-11-22 | 0 | 0% | None | None | 600 | 0 | -600
Mahmood | AI | 2024-11-22 | 0 | 0% | None | None | 250 | 0 | -250
Sadiqul | Django | 2024-11-22 | 0 | 0% | None | None | 600 | 0
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
imadinteractive
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pappu | Figma | 2024-11-22 | 0 | 0% | None | None | 500 | 0 | -500 | -4600 | 0 | None
Rafi | Flutter | 2024-11-22 | 0 | 0% | None | None | 1900 | 0 | -1900
Shuvo | Node.js | 2024-11-22 | 0 | 0% | None | None | 1900 | 0 | -1900
Mahmood | AI | 2024-11-22 | 0 | 0% | None | None | 1000 | 0
None | None | 2024-11-22 | 0 | 0% | None | None | 300 | 0 | -300
dxteng
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pappu | Figma | 2024-11-22 | 0 | 100% | Deliverd | Jan | 380 | 0 | -380 | -2080 | 0 | None
Ibrahim | React.js | 2024-11-22 | 0 | 0% | None | Jan | 980 | 0 | -980
Ibrahim | Django | 2024-11-22 | 0 | 0% | None | None | 720 | 0 | -720
kielspicer84
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Fahad | AI | 2024-11-22 | 0 | 0% | None | None | 3700 | 0 | -3700 | -4000 | 0 | Inprogress
Rafi | Flutter | 2024-11-22 | 0 | 0% | None | None | 300 | 0 | -300 | -300 | 0 | None
rnichaelzhu
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Bijoy | None | 2024-11-22 | 0 | 100% | Deliverd | Jan | 280 | 0 | -280 | -560 | 0 | None
Bashar | None | 2024-11-22 | 0 | 100% | Deliverd | Jan | 280 | 0 | -280
egolden96
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Mir | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0 | 0 | 0 | None
None | None | 2024-11-22 | 0 | 0% | None | None | 0 | 0 | 0
nftking
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 0% | None | None | 300 | 0 | -300 | -1100 | 0 | None
Rafi | Flutter | 2024-11-22 | 0 | 0% | None | None | 450 | 0 | -450
Pial | Django | 2024-11-22 | 0 | 0% | None | None | 350 | 0 | -350
Fahad | AI | 2024-11-22 | 0 | 0% | None | None | 300 | 0
aydtube
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Pial | Django | 2024-11-22 | 0 | 0% | None | None | 2000 | 2000 | 0 | 0 | 0 | None
agcourt
Developer name | Category | End Date | Remaining Date | Progress percentage | Individual Delivery status | Delivery Month | Assign Price | Per Milestone Total Price | Price Remain Per MileStone | Total Remaining Price MIleStone | Total Price | Project Delivery Status
Nil | Figma | 2024-11-22 | 0 | 0% | None | None | 100 | 0 | -100 | -550 | 0 | None
Shakil | React.js | 2024-11-22 | 0 | 0% | None | None | 225 | 0 | -225
Rafi | Flutter | 2024-11-22 | 0 | 0% | None | None | 225 | 0 | -225
Pial | Django | 2024-11-22 | 0 | 0% | None | None | 100 | 0
Formulas:
Remaining Date = MAX(0, [End Date]-TODAY())

## Sheet7
| Figma show krbo and flow buijha next kaj krbo. 3 din pore meeting then delivery | adamos007 | Done
Tyler B | Full flow sesh krte parben 3 din | Alanbrb | Pial vaier flow buijaile 1 din 10 tarikh meeting
fradituri | Done | dxteng | Done
dianadiaz12 | 30 % done meeting call | imaidnteractive
nftking
MIke

## Sheet6
Amd | Integration | 560
albertolorente | Integration | 1600
kielspicer84 | Model | 800
shayne_philiber | Integration | 1200
Postyxbt | Integration | 800
adamos007 | Figma+Frontend | 960 + 1040
mikenieciecki | Figma+Frontend | 1040 + 1360
agcourt | Full | 640
Alanbrb | Figma+Frontend
Tyler B | Figma+Frontend | 1600
fradituri | Figma+Frontend
dianadiaz12 | Figma+Frontend | 1440 + 1920
Abdulai556 | Figma+Frontend | 800 + 1640
mrrc12 | Full | 400
davisdebard
dxteng | full | 2080
imadinteractive | Figma | 1600
nftking
rnichaelzhu

## Developer KPI
Developer Name | Month 1 | Month 1 Extra | Month 2 | Month 2 Extra | Month 3 | Month 3 Extra | Total Gain KPI | Total Extra
Nil | 700 | -451 | 0 | -1151 | 0 | -1151 | 700 | -2753
Shakil | 300 | -851 | 0 | -1151 | 0 | -1151 | 300 | -3153
Rafi | 900 | -251 | 0 | -1151 | 0 | -1151 | 900 | -2553
Pial | 0 | -1151 | 0 | -1151 | 0 | -1151 | 0 | -3453
Ibrahim | 1180 | 29 | 0 | -1151 | 0 | -1151 | 1180 | -2273
Sadiqul | 0 | -1151 | 0 | -1151 | 0 | -1151 | 0 | -3453
Shuvo | 0 | -1151 | 0 | -1151 | 0 | -1151 | 0 | -3453
Fahad | 0 | -1151 | 0 | -1151 | 0 | -1151 | 0 | -3453
Rafsun | 0 | -1151 | 0 | -1151 | 0 | -1151 | 0 | -3453
Mir | 650 | -501 | 0 | -1151 | 0 | -1151 | 650 | -2803
Bijoy | 1230 | 79 | 0 | -1151 | 0 | -1151 | 1230 | -2223
Pappu | 1140 | -11 | 0 | -1151 | 0 | -1151 | 1140 | -2313
Mahmood | 0 | -1151 | 0 | -1151 | 0 | -1151 | 0 | -3453
Ramisa
Bashar | 480 | -671 | 0 | -1151 | 0 | -1151 | 480 | -2973

## Team Information
ca | Designation | Phone Number | Email
Nil | UI/UX | 01964071196 | nilutpalmajumder01@gmail.com | 19193
Rafi | Flutter Developer | 01959843534 | raihanrafi992@gmail.com | 19166
Shakil | Front-end Developer | 01814265294 | shakil57375@gmail.com | 19199
Pial | Backend Developer | 01796331459 | khpial27@gmail.com | 19181
Ibrahim | Backend Developer | 01746185116 | mdibrahimkhalil516@gmail.com | 19234
Shuvo | Backend Developer | 01795905178 | shuvo83qn@gmail.com | 19179
Sadiqul | Backend Developer | 01706711482 | mdsadiqulislam446@gmail.com, | 19233
Fahad | AI Developer | 01632701883 | istiaqahmmedfahad@gmail.com | 19125
Rafsun | AI Developer | 01837523658 | ahmadrafsun001@gmail.com
Showrav | Flutter Developer | 01616474076 | showravofficial@gmail.com
Ramisa | AI Developer | 01747275978 | ramisa.sharar377@gmail.com
Bashar | AI Developer | 01536162503 | mailto:abul35-2002@diu.edu.bd | 19250
| UI/UX | 01405366393 | pappyroy6393@gmail.com | 19256 | pappu29411
Mahmood | AI Developer | 01554557486 | hasanmahmudnayeem3027@gmail.com | 19253 | 7878
Bijoy | Front-end Developer | 01624393921 | bijoymamud.09@gmail.com | 19257 | 7858
Sajib | UI/UX | 1624393921 | sajibahhamed@gmail.com | 19294